East of England  Financial Capability and Inclusion Project

Costing Financial Capability Projects

Introduction

Estimating the cost of running financial capability sessions can be difficult, especially if you are relatively new to this type of work. To help you in developing a realistic budget for your work a worksheet follows which will help as a prompt to calculating the costs that are specific to the training / project that you plan to deliver.

Remember costs are not necessarily the same as the amount you charge or request funding for:

- You may be developing the capacity of your organisation through financial capability and be prepared to invest time and resources which are not immediately recoverable– in this case you can still tell the funder about your in kind contribution

- Alternatively you may have a lot of experience and resources that you can draw on and can seek to negotiate a higher price than cost, if this is still offering good value for money

Particular care is needed in budgeting when you are committing to deliver to a specific number of learners.  Our experience shows a wide range of variation in the numbers of people reached – depending on their needs, location and the barriers to participation that they may face.

For example it is much easier to predict the number of frontline workers you will train in an organisation when the session is being provided as part of their professional development than it would be offering an open session at a drop in for people with mental health needs.

To help you cost and price your work more accurately you may therefore find the worksheet below helpful. Do consider the hours of time taken by your staff /volunteers as well as items to be purchased. Where volunteers are used their expenses and support should be included as a cost but their time can be shown as an in kind contribution, similarly any free venues, resources can be included. Demonstrating this “in kind” contribution to the project can be important in influencing funders.

We hope you find this worksheet useful and we would welcome your feedback and ideas to develop this resource further based on your experience of delivery.

For feedback please contact beth.bell@citizensadvice.org.uk

December 2010

Worksheet

|  | Hours / £ | In kind | Notes |
| --- | --- | --- | --- |
| Staff costs |  |  |  |
| Induction and training |  |  | If you are recruiting new staff include their recruitment and induction costs as well as ongoing development and supervision costs. Citizens Advice regularly offers training in Delivering Financial Capability to forum members and details can be obtained through your Regional forum lead. Resources for other aspects of project delivery can be found at www.financialskillsforlife.org.uk. |
| Design training materials |  |  | Consider what resources can be reused from other sources – materials are available from a wide range of sources, e.g. Financial Capability Forums, Citizens Advice, CFEB, PFEG, NIACE, Chartered Institute of Housing, Barclays, Nationwide. Contact your Forum lead to find out if there are other organisations who have experience of this type of delivery that you could share ideas with or search our Bureau Activities Summary at www.financialskillsforlife.org.uk |
| Outreach to potential beneficiaries |  |  | This can take a significant amount of time. The amount of outreach depends on : - Who you are delivering to, e.g. frontline workers all from one organisation will take less time than engaging more diverse community groups - How extensive your existing contacts and networks are - How hard the “sell” is – a face to face session before delivery is always a good idea to agree desired outcomes and identify specific learner needs |
| Training delivery |  |  | This depends on the length of the training and whether it is being run on a one off or regular basis. Time should include preparation, session and follow up time. An organisation who is already experienced in financial capability can probably allow less time. Consider the hourly costing depending on whether you are using paid staff, consultants or volunteers. Also consider the appropriate size of the group– are one to one sessions needed? |
| Monitoring and evaluation |  |  | This will depend on the outputs / outcomes agreed with the funder. They can be relatively simple, e.g. number trained/sessions delivered/learner hours/ participant feedback, but funders increasingly want to know what difference the training has made and this may mean some follow up work and additional expenses, e.g. postal/telephone surveys after 6-12 weeks |
| Travel expenses |  |  | This should include staff travel expenses for outreach, delivery and follow up activity |
| Management and Supervision |  |  | Include any other staff costs associated with running the project ( please note not all funders will cover these but again you should be aware of the resources required) |
| Volunteer costs |  |  |  |
| Expenses |  |  | Travel, lunch and any other expenses permitted within your volunteer involvement policy – don’t forget if volunteers are likely to be delivering in pairs to factor in additional costs |
| Training |  |  | Access to relevant training for the volunteers to support their participation |
| Support |  |  | Time needed to offer volunteers involved in delivery appropriate support and guidance |
| Beneficiary costs |  |  |  |
| Identified support needs / permissible expenses |  |  | Learner needs should be carefully considered, especially when working with those groups who are more vulnerable to exclusion. Consider what will enable participation –e.g. translation/ interpretation costs, travel costs (especially in rural areas), childcare costs; resources that need to be adapted, e.g. materials produced in large print or easy read, any venue adaptations, e.g. hearing loop, support that will be needed by participants in session, e.g. getting their support workers involved as well. Potentially these costs can be very high but may also be realistic if you intend to deliver training to people who face significant barriers to participation – getting these costs included will of course also depend on the funders priorities |
| Other costs |  |  |  |
| Venue hire |  |  | This will depend on the needs / location of your beneficiaries. We know that financial capability is best delivered in settings where people feel comfortable and at ease so if working with community groups try and go to where they already meet rather than hiring somewhere else (which may have added complications re travel, adaptations, etc). Similarly frontline worker organisations may well be able to offer you a free venue. Alternatively contact your local Council or CVS for ideas re low cost venues. |
| Publicity / Resources |  |  | Advance publicity does not need to be glossy or expensive looking. The key to involving people is in the contacts made rather than distributing leaflets. Email is very effective for working with groups. Training resources can be photocopied and end of session certificates are often appreciated. You may also want to provide pens, paper, calculators, depending on the content of your session and low cost prizes, e.g. chocolate money often work well. More expensive resources include hand held answering devices and /or laptops –including these depends on learner needs– they are more likely to enable participation / embed learning than increase project outputs and will therefore need to be clearly justified. |
| Office costs |  |  | You should make an allowance for your contribution to office costs as appropriate |

Remember – this is not a definitive guide to all costs that may arise in the course of delivering training but it should provide a handy (and realistic!) reminder of what to consider.